## Slide 1: Creedmoor Powder Dispenser

## Slide 2: Weekly progress (Hardware)

## Slide 3: Weekly progress (software)

## Slide 4: Week 1 (5-Jan to 11-Jan) Austin Stecklein
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) | 0 | 0
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) | 100 | .5
Team Complete: Project Task Template (A Gantt Chart) (Conditions or tasks that must be completed, work that needs to be done) | 0 | 0
Flow charts for hardware and software | 100 | 5.5
Hours on task during the week (On track ≥ 13 / wk) | 6
Total hours on task so far this semester (On track ≥ 13 hrs) | 13
Example Project Objective / Mission Statements
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $XXX USD and for less than 600 people-hours.
For ideas, also read Mission Questions in I-Learn | Content | Resources | Mission Questions

## Slide 5: Progress made during the week (Log) (What I did)
Created general software and hardware layout
Researched hardware parts

## Slide 6: Difficulties encountered during the week (What I did not do and why)
Defining scope of project

## Slide 7: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Selecting processor for project with rest of the group. | 1/14/21 | 1
Researching drivers for stepper motors | 1/16/21 | 2
developing backend framework with chosen programming language | 1/26/21 | 10
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 8: How can we help you achieve your goals?
Understanding more of the final product

## Slide 9: Week 1 (5-Jan to 11-Jan) Jonathan Phillips
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) |  | 
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) |  | 
Team Complete: Project Task Template (A Gantt Chart) (Conditions or tasks that must be completed, work that needs to be done) |  | 
Hours on task during the week (On track ≥ 13 / wk) | 
Total hours on task so far this semester (On track ≥ 13 hrs) | 
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $XXX USD and for less than 600 people-hours.

## Slide 10: Progress made during the week (Log) (What I did)
Created a Gannt Chart for the layout for the hardware and software
Researched different LCDs that could be used for the touch screen display

## Slide 11: Difficulties encountered during the week (What I did not do and why)
Did not order the LCD screen yet due to it needing to be approved first by the group

## Slide 12: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Finalize parts for the project and order them | 1/13/22 | 1
Start Development on the Front End framework | 1/26/22 | 12
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 13: How can we help you achieve your goals?
Do you have a preference on what the screen will be?
Elecrow
Kuman
GeeekPi

## Slide 14: Week 1 (5-Jan to 11-Jan) Dale Andreoli
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) | 0 | 0
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) | 100 | 1
Team Complete: Project Task Template (A Gantt Chart) (Conditions or tasks that must be completed, work that needs to be done) | 35 | 1
Hours on task during the week (On track ≥ 13 / wk) | 5
Total hours on task so far this semester (On track ≥ 13 hrs) | 5
Example Project Objective / Mission Statements
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $XXX USD and for less than 600 people-hours.
For ideas, also read Mission Questions in I-Learn | Content | Resources | Mission Questions

## Slide 15: Progress made during the week (Log) (What I did)
Researched potential processors

## Slide 16: Difficulties encountered during the week (What I did not do and why)
Determining what we need to do and how to divide it

## Slide 17: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Research potential processors | 1/14/21 | 2
Collaborate as a group to determine which processors would be best | 1/16/21 | 4
Research methods to implement necessary drivers | 1/26/21 | 6
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 12

## Slide 18: How can we help you achieve your goals?
Clarify/Answer Questions

## Slide 19: Week 1 (5-Jan to 11-Jan) Colby Hatton
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) |  | 
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) |  | 
Team Complete: Project Task Template (A Gantt Chart) (Conditions or tasks that must be completed, work that needs to be done) |  | 
Hours on task during the week (On track ≥ 13 / wk) | ~5
Total hours on task so far this semester (On track ≥ 13 hrs) | ~5
Project Objective / Mission Statements
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $XXX USD and for less than 600 people-hours.
For ideas, also read Mission Questions in I-Learn | Content | Resources | Mission Questions

## Slide 20: Progress made during the week (Log) (What I did)
Helped create general software and hardware layout
Purchased leadership book
Preliminary research

## Slide 21: Difficulties encountered during the week (What I did not do and why)
No problems yet

## Slide 22: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Find, compare, and form opinions on the correct processor for our project. | 1/14/22 | 4
Selecting processor for project with rest of the group. | 1/16/22 | 1
Obtain, test, and experiment with given hardware | 1/16/22 | 3
Class time, presentations, workbook, etc. | 1/16/22 | 4
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 23: How can we help you achieve your goals?
Communication - Ensure lines work and communication is clear.

## Slide 24: Week 1 (5-Jan to 11-Jan) John Stinger
Goal/Task | % Done | Hours (Act.)
Everyone Complete Leadership Foundation: Clarify Purpose (p. 32-33), Team Purpose Statement (p. 34), Voice Finder (p. 64-67), Your Contribution Statement (p. 68), Win-Win Performance Agreement (p. 76) |  | 
Team Complete: Project Objective / Mission Statement (clear and concise, <25 words, see example below) |  | 
Team Complete: Project Task Template (A Gantt Chart) (Conditions or tasks that must be completed, work that needs to be done) |  | 
Hours on task during the week (On track ≥ 13 / wk) | 12
Total hours on task so far this semester (On track ≥ 13 hrs) | 12
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $XXX USD and for less than 600 people-hours.

## Slide 25: Progress made during the week (Log) (What I did)
Researched different processors and possible boards to use in the project.
Atmel ARM based microprocessor would be best.
Raspberry Pi Zero 2 would be effective and affordable, but generally unavailable.
Do we want a commercially available board?

## Slide 26: Difficulties encountered during the week (What I did not do and why)
Select a specific processor. Needed to meet with the team to discuss options.

## Slide 27: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Select a Processor |  | 1
Define the exact scope of the project |  | 2
Define individual roles |  | 1
Purchasing a Board |  | 2
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 

## Slide 28: How can we help you achieve your goals?
More than one day to do research and meet with the team.