## Slide 1: Week 5 (2-Feb to 8-Feb)

## Slide 2: Week 5 (2-Feb to 8-Feb) Austin Stecklein
Goal/Task | % Done | Hours (Act.)
Investigating hardware | 100 | 3
Finish database | 99 | 4
Backend events | 75 | 6
Hours on task during the week (On track ≥ 13 / wk) | 13
Total hours on task so far this semester (On track ≥ 62 hrs) | 56

## Slide 3: Progress made during the week (Log) (What I did)
Found that voltage regular to be the problem. Will take these lessons learned for future hardware
Finish database and interface for the GUI.
Continued to work on the PID and physical events.

## Slide 4: Difficulties encountered during the week (What I did not do and why)
None

## Slide 5: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Finish backend events and start testing them with replacement beagle bone (lower voltage this time) | 2/16/2021 | 6
Finish PID and start experimenting with finding the best coefficients | 2/16/2021 | 5
Start merging GUI and backend | 2/16/2021 | 4
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 15

## Slide 6: Week 5 (2-Feb to 8-Feb) John Stinger
Goal/Task | % Done | Hours (Act.)
Continue to work on the board schematic |  | 4
Continue to work on the board layout |  | 4
Other |  | 4
Hours on task during the week (On track ≥ 13 / wk) | 12
Total hours on task so far this semester (On track ≥ 62 hrs) | 51

## Slide 7: Progress made during the week (Log) (What I did)
Board development
Found different connectors
Started testing speakers

## Slide 8: Difficulties encountered during the week (What I did not do and why)
none

## Slide 9: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Continued Development of the board | Ongoing | 7
Research how to design better board drivers |  | 3
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 12

## Slide 10: How can we help you achieve your goals?
Continued Support

## Slide 11: Week 5 (2-Feb to 8-Feb) Colby Hatton
Goal/Task | % Done | Hours (Act.)
Schematic Work | 85% | 10
Layout | 5% | 1
Parts/Resarch/Testing | 80% | 2
Hours on task during the week (On track ≥ 13 / wk) | 
Total hours on task so far this semester (On track ≥ 62 hrs) | 51

## Slide 12: Progress made during the week (Log) (What I did)
Preformed MicroSD boot, verified speaker arrangement, prepared pin layout

## Slide 13: Difficulties encountered during the week (What I did not do and why)
Finding a good motor driver

## Slide 14: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Obtain Motor Driver | Ongoing | 13
Finish Schematic |  | 
Contuine Layout |  | 
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 15: How can we help you achieve your goals?
Continued Support, consistently updated line/signal list

## Slide 16: Week 5 (3-Feb to 9-Feb) Dale Andreoli
Goal/Task | % Done | Hours (Act.)
Find or create a touch keyboard module to slot into the GUI | 80% | 5
Collaborate with Jonathan and Austin on GUI implementation |  | 9
Hours on task during the week | 14
Total hours on task so far this semester | 56
Project Objective / Mission Statements
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $1000 USD and for less than 600 people-hours.

## Slide 17: Progress made during the week (Log) (What I did)
Found a keyboard that should suit our needs after some modification
Refactored some of the GUI code to better apply principles of abstraction
Collaborated with Jonathan and Austin on GUI implementation

## Slide 18: Difficulties encountered during the week (What I did not do and why)
Jonathan and I were getting some errors from the library as we tried to put the GUI code into different files

## Slide 19: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Finish implementing the keyboard |  | 3
Collaborate with Jonathan and Austin on what GUI pages to implement next |  | 9
Estimated time needed to work on goals for this coming week | 12

## Slide 20: Week 5 (2-Feb to 8-Feb) Jonathan Phillips
Goal/Task | % Done | Hours (Act.)
Front End | Ongoing | 11
Hours on task during the week (On track ≥ 13 / wk) | 11
Total hours on task so far this semester (On track ≥ 62 hrs) | 51

## Slide 21: Progress made during the week (Log) (What I did)

## Slide 22: Difficulties encountered during the week (What I did not do and why)
Python doesn’t like circular imports

## Slide 23: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Front End | Ongoing | 13
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 24: How can we help you achieve your goals?
Continued Support