## Slide 1: Week 6 (9-Feb to 15-Feb)

## Slide 2: Week 6 (9-Feb to 15-Feb) Austin Stecklein
Goal/Task | % Done | Hours (Act.)
Finish backend events and start testing them with replacement beagle bone | 50 | 6
Finish PID and start experimenting with finding the best coefficients | 25 | 3
Start merging GUI and backend | 50 | 3
Coordinating GUI and hardware direction | NA | 2
Hours on task during the week (On track ≥ 13 / wk) | 14
Total hours on task so far this semester (On track ≥ 75 hrs) | 70

## Slide 3: Progress made during the week (Log) (What I did)
Started merging backend and frontend
Testing backend on the beaglebone
Determining realistic deliverable with time frame

## Slide 4: Difficulties encountered during the week (What I did not do and why)
GUI change

## Slide 5: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Finish merging frontend and backend | 2/23 | 6
Get prototype working | 2/23 | 6
start documentation | 2/23 | 10
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13

## Slide 6: Week 6 (9-Feb to 15-Feb) Colby Hatton
Goal/Task | % Done | Hours (Act.)
Schematic | 90% | 4
Layout | 10% | 5
Parts/Research/Testing | 80% | 2
Hours on task during the week (On track ≥ 13 / wk) | 13
Total hours on task so far this semester (On track ≥ 75 hrs) | ~75

## Slide 7: Progress made during the week (Log) (What I did)
Began board layout, imported components, defined board shape, took measurements for positioning, and cried at the rats nest that will have to be resolved.

## Slide 9: Difficulties encountered during the week (What I did not do and why)
Motor driver (See Johns Presentation)

## Slide 10: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Continue Board Layout |  | 
Finalize Components |  | 
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 

## Slide 11: How can we help you achieve your goals?
Be ready for questions about components/layout

## Slide 12: Week 6 (9-Feb to 15-Feb) John Stinger
Goal/Task | % Done | Hours (Act.)
Driver Research |  | 5
Board Development |  | 3
Discussions and Meetings |  | 3
Hours on task during the week (On track ≥ 13 / wk) | 11
Total hours on task so far this semester (On track ≥ 75 hrs) | 62

## Slide 13: Progress made during the week (Log) (What I did)
For example: Resources found (links, manuals), Designs created, Decisions made and corresponding rational, Photos of prototype progress, etc.
The current NEMA 14 motor is rated for 4.2 V
Looking at drivers with ~ 5 – 30 V
Found open-source driver controllers

## Slide 14: Difficulties encountered during the week (What I did not do and why)
Trying to determine the proper voltage

## Slide 15: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Have a specific driver chip selected |  | 2
Continue with board development |  | 10
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 

## Slide 16: How can we help you achieve your goals?
Continue to be available for questions

## Slide 17: Week 5 (10-Feb to 16-Feb) Dale Andreoli
Goal/Task | % Done | Hours (Act.)
Create Load page | 75 | 2
Finish Home page |  | 4
Remake home page according to the new design | 90 | 8
Hours on task during the week | 14
Total hours on task so far this semester | 70
Project Objective / Mission Statements
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2021 with a prototyping budget of $1000 USD and for less than 600 people-hours.

## Slide 18: Progress made during the week (Log) (What I did)
Remade Home page according to the new design from Christian
Started Load page (old design)

## Slide 19: Difficulties encountered during the week (What I did not do and why)
None

## Slide 20: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Implement Load screen on the new design |  | 5
Implement Save screen |  | 5
Collaborate with Jonathan to implement buttons from the design |  | 2
Estimated time needed to work on goals for this coming week | 12

## Slide 21: Week 6 (9-Feb to 15-Feb) Jonathan Phillips
Goal/Task | % Done | Hours (Act.)
Front end – How to make Images into Buttons | 100 | 2
Front end – Splicing the buttons from Christian's design | 20 | 1
Front end – General Progression |  | 10
Hours on task during the week (On track ≥ 13 / wk) | 12
Total hours on task so far this semester (On track ≥ 75 hrs) | 65
Power Scale Dispenser:
Design, build, and test the electronics for the dispenser with a touch screen display and controlling two stepper motors by April 6, 2022, with a prototyping budget of $1000 USD and for less than 600 people-hours.

## Slide 22: Progress made during the week (Log) (What I did)

## Slide 23: Difficulties encountered during the week (What I did not do and why)
The same button cannot raise and depress itself. It can do either or, but not both.

## Slide 24: Goals for this coming week (Ones that move the project forward the most)
Goal/Task | Stop Date (Est.) | Hours (Est.)
Front end – Splicing Images from Christian's design | 2/23/22 | 2
Front end – Implementation of images as buttons | 2/23/22 | 5
Front end – General Progression | 4/1/22 | 6
Estimated time needed to work on goals for this coming week (typ. 13 hrs) | 13